## M-DART Product Backlog
I, as a <role>, | I need <requirement> | so that <benefit> | Subsystem | Size (in hours) | Item ID | Sprint Sequence No | Priority | Status | Comments
Developer | A development environment | I can start programming | Development | 16 | 01-001 | 1 | High | ON BLOG | Mandriva 2009.1 Linux with GNAT 2009
Author | Maintain the Blog | I keep a discussion on the web | Blog | 400 | 01-002 | ALL | Medium | OPEN
Developer | Familiarize myself with the programming environment | I can start programming effectively | Development | 8 | 01-003 | 1 | High | ON BLOG | GPS 4.3.1 and Kdevelop
Developer | Familiarize myself with the programming language | I can start programming effectively | Development | 40 | 01-003 | 1 | High | ON BLOG | Ada 2005
Developer | Implement a basic Windows Package | I can view pictures being rendered | Viewing | 20 | 02-001 | 2 | High | ON BLOG
Developer | UML Diagrams for the Basic Types & Utility Classes | I have a clear class structure to work from | Development | 4 | 03-001 | 3 | High | OPEN | Visio?
Developer | Basic Types & Utility Classes | I have a sound foundation to build my rendering algorithms | Development | 40 | 03-002 | 3 | High | OPEN
Author | Write the draft Basic Design Chapter for the book |  | Book | 16 | 04-001 | 4 | High | OPEN

## Completed Backlog Items
I, as a <role>, | I need <requirement> | so that <benefit> | Subsystem | Size (in hours) | Item ID | Sprint Sequence No | Priority | Status | Comments

## Enumerations
Viewing | Developer | MUST | IMPL
Modelling | Author | NICE | TESTED
Rendering | User | IDEA | ON BLOG
Book |  |  | IN BOOK
Blog |  |  | OPEN
Development