## Sprint 1
M-DART Project
The Development of a Ray Tracing System in the Ada 2005 Programming Language
Goal: Implementation of Utility Classes
Product Backlog Item | Task | Estimate | Assigned To | Status | Remain | Comments
03-001 | Design a UML Diagram for the Basic Types | 2 | Marinko |  | 2
03-001 | Design a UML Diagram for the Vector & Matrix Types | 3 | Marinko |  | 3
03-002 | Implement the Basic Types as an Ada 2005 package | 2 | Marinko |  | 2
03-002 | Implement the Vector & Matrix Types as an Ada 2005 package | 16 | Marinko | Completed | 16
03-002 | Implement the Vector & Matrix Types as an Ada 2005 package | 16 | Marinko |  | 16
TOTAL |  | 23 |  |  | 23

## Burndown Chart
Date | Day | Actual (h) | Plan (h) | Baseline (h)
2009-04-21 | 0 | 105.5 | 105.5 | 0
2009-04-22 | 1 |  | 94.95
2009-04-23 | 2 |  | 84.4
2009-04-24 | 3 |  | 73.85
2009-04-27 | 4 |  | 63.3
2009-04-28 | 5 |  | 52.75
2009-04-29 | 6 |  | 42.2
2009-04-30 | 7 |  | 31.65
2009-05-01 | 8 |  | 21.1
2009-05-04 | 9 |  | 10.55
2009-05-05 | 10 |  | 1.4211e-14

## Team Capacity
M-DART Project
The Development of a Ray Tracing System in the Ada 2005 Programming Language
Team |  | Remain (d) | 0
| Alloc (%) | Adjust (d) | Remain (h)
Marinko |  |  | 0
0
Total |  |  | 0
Remain (h)

## Enums
Statuses | Resources
Pending | Marinko
In Progress
Completed
Blocked